Document Purpose

This document was produced by the FAME Programme to provide guidance and practical examples to all Local Authorities/Partner Agencies for an implementation of Multi-Agency working.  All documents are the property of FAME National Project, and to access these documents you have agreed to the terms and conditions set out in the accessing of these products from the FAME website.

For a further description of this document please see the Product Definition below stating exactly what the product is.  For more in depth explanation and guidance please see the FAME "How to Implement and Sustain a Multi-Agency Environment".

Business Case:

a document which sets out the justification for undertaking a project, based on the estimated cost of development and implementation against the risks and expected business benefits and savings.

# Executive Summary

In the past Children with Disabilities or complex health needs on average received 18 different assessments of their needs. Each dealt with one part of the child’s life or needs without providing an overall view of “the child”. The assessments were not co-ordinated and could be simultaneous or sequential. Each assessor asked similar questions resulting in parents and carers having to repeat “their story”. The Single Assessment Process ensures that assessments are co-ordinated, professionals share information, are therefore better informed and the parent carer needs to explain less. The system identifies a professional to co-ordinate the assessment and plan, reducing the burden on the parent or carer. It helps to co-ordinate reviews across three agencies.

# Reason for project

The Children Act 1989 requires Local Authorities to hold a register of Children with Disabilities. This information was to be collected from parents on a voluntary basis and used to plan local services. Newcastle like many other Local Authorities found that few parents volunteered to be part of the register and the information gathered was insufficient to plan services. Parents stated that services were not co-ordinated across agencies, which meant the parent became the co-ordinator. Parents in Newcastle wanted professionals to talk to each other so that the parent had to “tell their story” only once.

# Options for consideration

Option 1 – ‘Do Nothing’ - Social Services and Health have based some staff together, which is developing some systems to co-ordinate some services for some children with disabilities. The Local Authority register has not been updated for sometime and a publicity campaign may increase take up by parents. - Newcastle is an ISA Trailblazer area and may produce improved information on children on which to plan services. Risks - The co-ordination is not systematic and is based on the co-location of professionals. If one of the agencies changes its estate management policy the co-location and co-ordination will fail. - The co-ordination is based on the good working relationship between the teams and individuals within the teams. This may change. - The teams involved only cover 10% of the Children with Disabilities in the city. - Previous publicity campaigns have resulted in up to 150 children being registered. Statistically there should be 2223 Children with Disabilities in Newcastle. - The ISA Trailblazer will initially only cover a small part of the city. Gaining permissions to use the information would be difficult. - The view across agencies was that this option would not produce positive results.

Option 2 – ‘Create an electronic register from information currently held across agencies’ - Some work has been completed to link IT systems in Health, Education and Social Services, which would create a shared database of Children with Disabilities. - This would allow professionals to identify if a child was known to other agencies and managers could use the anonymised, aggregated data to plan services. Once professionals knew others were involved they could then work together. - The system would hold a minimum data set and could be developed “in house” by the Local Authority. Risks - Once professionals identified that other agencies are involved the emphasis would still be on the parents to co-ordinate services. Parents would still have to “tell their story” to each professional involved. The system may not meet the needs of professionals and they would not be motivated to use it. Any gaps in the data would make strategic planning difficult. The success of the system would be based on accuracy and efficiency of the current IT systems. The introduction of NPFIT may make the system unviable. This may replicate the work of the ISA Trailblazer. The view across agencies was that while this may improve strategic planning the benefits to children and families would be “patchy” at best.

Option 3 – ‘Develop a reusable Framework for multi-agency teams that provide integrated services to Children with Disabilities.’ This would involve changing the referral and assessment processes of teams across Health, Education and Social Services. Operational and strategic managers across the three agencies had worked towards a more integrated approach to services and had applied for Children’s Trust status on this basis. Professionals would need to ‘let go’ of old systems and work together to develop new ones. The new system would require integration with current systems used by the agencies. Risks The professionals may not agree to the practice changes. It may not be possible to obtain agreement to the information sharing from the agencies or parents. It may not be possible to integrate the systems. The costs may be too high (financially and organisationally).

# Benefits - assessment for each option

## OPTION 1 – Do Nothing

| OPTION 1 – Do Nothing | Benefits | Strategic Objectives | Measure | Current Performance | Target |
| --- | --- | --- | --- | --- | --- |
| Citizen | Some services to Children with Disabilities (CwD) will be better co-ordinated. | Co-ordinate service delivery. | Customer satisfaction. Co-ordinated plans | No co-ordinated plans | 10% of assessments and plans co-ordinated by 2005 |
| Business Process | Use the information gathered through the data base to plan strategically. | Plan strategically based on accurate information about need. | Register provides information for strategic planning | Register not used | Information from database used in 2005 Children’s Services plan. |
| Financial | Individual and strategic plans focussed on need. | Co-ordinate service delivery. Plan strategically based on accurate information about need. | Individual plans show evidence of co-ordinated assessment. Strategic plans include evidence of need based on information from the register. | Little co-ordination Register not used | 10% of assessments and plans co-ordinated by 2005 Information from database used in 2005 Children’s Services plan. |
| Learning & Growth | Services change to focus on identified need. | Plan strategically based on accurate information about need. | Strategic plans include evidence of need based on information from the register. | Register not used | Information from database used in 2005 Children’s Services plan. |

## OPTION 2 – ‘Create an electronic register from information currently held across agencies’

| OPTION 2 – Create Database | Benefits | Strategic Objectives | Measure | Current Performance | Target |
| --- | --- | --- | --- | --- | --- |
| Citizen | Services would be planned based on need | Identify all CwD | Register contains 2000+ entries | 180 entries | 2000+ entries by April 2004 |
| Business Process | Some Joint working Improved targeting in service provision Shared planning across Health, Education and Social Services | Provide a co-ordinated service Plan service provision based on register Reduce duplication | Customer satisfaction Strategic Plan based on need and trends | No co-ordinated plans Plan based on perceived need and priorities | Co-ordinated service to 100 families Strategic Plan based on identified need by 2005 |
| Financial | Targeted services to improve efficiency | Target services on agency priorities | Increased customer satisfaction, savings through efficiencies | Services targeted on perceived need, evidenced through information from register | 5% savings by 2006 |
| Learning & Growth | Increased joint working | Share skills across agencies | Multi-agency teams | Some co-ordination of services | Professionals work across boundaries 2005 |

## OPTION 3 – ‘Develop a reusable Framework for multi-agency teams that provide integrated services to Children with Disabilities.’

| OPTION 3 – Create reusable framework | Benefits | Strategic Objectives | Measure | Current Performance | Target |
| --- | --- | --- | --- | --- | --- |
| Citizen | Services to CwD will be co-ordinated Services planned on the basis of need | Create multi-agency referral assessment and planning for CwD Identify all CwD | Shared case records Number of children on system | None None | 300 by 2005 300 by 2005 |
| Business Process | Joint working for most complex cases Improved targeting in service provision Shared planning for individual children across Health, Education and Social Services | Provide co-ordinated services to CwD Plan service provision based on information gathered through assessments Reduce duplication | Customer satisfaction Service Plan based on needs and trends Shared plans | None Plan based on evidence of need and priorities Few plans | 150 by 2005 Strategic Plan based on need by 2006 150 by 2005 |
| Financial | Targeted services to improve efficiency | Target services using priorities set in individual plans Reduce duplication of work | Use of individual plans to inform multi-agency service plan One assessment per child | Not used Few | Use 150 plans by 2005 150 by 2005 |
| Learning & Growth | Increased joint working Pass on lessons to wider service areas | Share skills across agencies Develop Children’s Trust across agencies | Multi-agency assessments, plans and reviews Joined up strategic plan | Few Consultation between agencies with single agency plan | 150 by 2005 Integrated plan |

# Costs

| ## Project Expenditure | Option 1 ‘Do Nothing’ | Option 2 ‘Register’ | Option 3 ‘Case Record’ |
| --- | --- | --- | --- |
| Programme Management & Support | £0.00 | £0.00 | £5,000 |
| Project Management & Support | £0.00 | £25,000 | £56,191 |
| User and Customer Consultation | £0.00 | £3,000 |  |
| Procurement Expertise | £0.00 | £0.00 |  |
| Publicity | £5,000 | £2,000 |  |
| Training | £0.00 | £20,000 | £6,110 |
| Hardware | £0.00 | £30,000 | £53,072 |
| Software | £0.00 | £45,000 |  |
| Development Resource - Internal | £0.00 | £0.00 | £8,000 |
| Development Resource - External | £0.00 | £0.00 | £111,537 |
| Other | £0.00 | £0.00 | £10,090 |
| Totals | £5,000 | £125,000 | £250,000 |

| ## Ongoing Operational Expenditure | Option 1 | Option 2 | Option 3 |
| --- | --- | --- | --- |
| Training | £0.00 | £5,000 | £0.00 |
| Capital Assets Management | £0.00 | £0.00 | £0.00 |
| System Maintenance | £0.00 | £15,000 | £0.00 |
| Bug fixes and upgrades | £0.00 | £0.00 | £0.00 |
| Totals | £0.00 | £20,000 | £0.00 |

# Risks, Issues for each option

## Risk/Issues Option 1 ‘Do Nothing’

| Risk / Issue | Likelihood | Impact | Overall Risk Rating | Action |
| --- | --- | --- | --- | --- |
| #### Services continue to be uncoordinated | #### 80% | #### 500,000 |  | #### Develop new system |
| #### Database is too small to use for planning purposes | #### 75% | #### 250,000 |  | #### Use paper based system |

## Risk/Issues ‘Register’

| Risk / Issue | Likelihood | Impact | Overall Risk Rating | Action |
| --- | --- | --- | --- | --- |
| #### System not used to co-ordinate services | #### 50% | #### 500,000 |  | #### Introduce training to improve |
| #### IT systems cannot be linked | #### 50% | #### 250,000 |  | #### Use paper based system |

## Risk/Issues Option 3

| Risk / Issue | Likelihood | Impact | Overall Risk Rating | Action |
| --- | --- | --- | --- | --- |
| #### Agencies do not agree to share information | #### 40% | #### 250,000 |  | #### Develop information sharing protocol with support of parents |
| #### IT systems cannot be linked | #### 50% | #### 500,000 |  | #### Use double entry |
| #### Professionals do not sign up to the assessment tool | #### 40% | #### 250,000 |  | #### Involve professionals in creating the assessment tool |

# Dependencies / Assumptions

| ## Option | Dependencies / Assumptions |
| --- | --- |
| ## Option 1 | Health and Social Services remain committed to joint location and co-ordinating services. Funding is available. |
| ## Option 2 | Data Protection issues could be solved. IT solutions can be developed ‘in house’. Education and Social Services committed to the project and funding. Each agency has a system to link to. |
| ## Option 3 | Each agency has a system. A multi-agency assessment tool is in place. Each agency has robust internal communication systems. Endorsement from DoH and DfES because it is a national programme. Sign up at a high level in all agencies. Data Protection issues could be resolved. Funding available. |

# Timescales

| ## Timescales Option 1 | Advertise and update register by July ‘04 |
| --- | --- |
| ## Timescales Option 2 | Information Sharing Protocol by March ‘04 Trial software, May ’04-July ’04 Full introduction of register by Oct ‘04 |
| ## Timescales Option 3 | Information Sharing Protocol and consultation by March ‘04 Pilot system April ’04-June ‘04 Full introduction by Sept ‘04 |

# Investment Appraisal and Evaluation for each option

## Option 1 Cost vs. Benefit Evaluation

| Costs over 1 year | Benefits Financial Over 1 year | Benefits Non-Financial Over 1 year | Overall Evaluation |
| --- | --- | --- | --- |
| £5,000 | None | Improved joint working | Low cost and little improvement to service |
|  |  | Increase number of children on register |  |

## Option 2 Cost vs. Benefit Evaluation

| Costs over 1 year | Benefits Financial Over 1 year | Benefits Non-Financial Over 1 year | Overall Evaluation |
| --- | --- | --- | --- |
| £125,000 | Less duplication of assessment work | Improved co-ordination of some services | Medium costs with improvements to efficiency |
|  | Resources more focussed on priorities | Better planning based on need |  |

## Option 3 Cost vs. Benefit Evaluation

| Costs over 1 year/s | Benefits Financial Over 1 year | Benefits Non-Financial Over 1 year | Overall Evaluation |
| --- | --- | --- | --- |
| £250,000 | Less duplication of assessment work | Services co-ordinated | High cost with increased likelihood of achieving changes in practice, organisation and strategic planning. Most likely option to improve outcomes for children |
|  | Resources more focussed on priorities | Improved strategic planning |  |
|  |  | Joint working, changes in practice |  |
|  |  | Shared plans lead to better outcomes for children |  |
|  |  | Improved inspection reports |  |